## ToDo
Number | Arrival Time | Type | Module | Item | Priority | Status
34 | 2005-06-29 | Bugfix | hosts.pl | Line 141: missing " at the end of the line. line starting | 5 | Done
33 | 38550 | Bugfix | import.pl | Error when importing config file (resources) | 5 | Done
9 | 2005-10-15 | Bugfix | NCPL_DATABASE.pm | Use html_urlencode for the action buttons | 5 | Done
16 | 2005-10-18 | Bugfix | NCPL_EXPORT.pm | active_check_enabled, passive_check_enabled | 5 | Done
17 | 2005-10-18 | Bugfix | services.pl | active_check_enabled, passive_check_enabled | 5 | Done
22 | 2005-10-27 | Bugfix | export.pl | Sessions timeout problem | 5 | Pending
23 | 2005-10-27 | Bugfix | MYSQL | Add "server_name" to primary keys | 5 | Done
30 | 2005-10-27 | Bugfix | GENERAL | Comboboxes: disabled items | 5 | Pending
24 | 2005-11-01 | RFE | MYSQL | Length of host_name/server_name fields (255 => 64 chars) | 4 | Done
25 | 2005-11-02 | RFE | MYSQL | General optimalisation of the database | 4 | Done
72 | 2005-10-27 | Bugfix | import.pl | Sessions timeout problem | 5 | Pending
51 | 2005-07-17 | RFE | hostextinfo.pl | New module: Host Extended Information | 3 | Done
54 | 2005-07-17 | RFE | hosts.pl | New module: Hosts | 3 | Done
42 | 2005-07-17 | RFE | users.pl | Password encryption (MD5) | 3 | Done
57 | 2005-07-17 | RFE | import.pl | Import: default path | 3 | Done
58 | 2005-07-17 | RFE | export.pl | Export: default path | 3 | Done
59 | 2005-07-17 | RFE | services.pl | New module: services.pl | 3 | Done
60 | 2005-07-17 | RFE | install.pl | New module: install new config + diff config files | 3 | Done
55 | 2005-07-17 | RFE | users.pl | Confirm password | 3 | Done
4 | 2005-10-20 | RFE | NCPL_EXPORT.pm | Check dependencies on export | 3 | In progress
5 | 2005-10-20 | RFE | GENERAL | Check dependencies on delete | 3 | Pending
26 | 2005-10-27 | RFE | servers.pl | Server type: central, distributed | 3 | Pending
7 | 2005-10-15 | RFE | consistency.pl | Complete rewrite of this module | 2 | Pending
10 | 2005-10-15 | RFE | NCPL_DATABASE.pm | doQueryDBI: dbh->do() implementation | 2 | Pending
11 | 2005-10-15 | RFE | NCPL_EXPORT.pm | Export config files in a separated directory | 2 | Done
12 | 2005-10-15 | RFE | install.pl | Installed config files in a separated directory | 2 | Done
13 | 2005-10-15 | RFE | install.pl | Choice of server you want to export | 2 | Done
28 | 2005-10-27 | RFE | NCPL_EXPORT.pm | Cleanup function for comma separated fields (sort, remove spaces) | 2 | Pending
40 | 2005-07-17 | RFE | statistics.pl | Adding extra tables | 1 | Done
31 | 2005-11-02 | RFE | install.pl | Confirmation screen before install and before sending email | 2 | Pending
41 | 2005-07-17 | RFE | GENERAL | Search capabilities | 1 | Pending
43 | 2005-07-17 | RFE | nagios.pl | New module: Reload/Restart nagios process | 1 | Pending
44 | 2005-07-17 | RFE | main.pl | New module: Main configuration file (nagios.cfg) | 1 | Pending
45 | 2005-07-17 | RFE | cgi.pl | New module: CGI configuration file (cgi.cfg) | 1 | Pending
46 | 2005-07-17 | RFE | htaccess.pl | New module: .htaccess file management | 1 | Pending
47 | 2005-07-17 | RFE | serviceextinfo.pl | New module: Service Extended Information | 1 | Pending
48 | 2005-07-17 | RFE | serviceescalations.pl | New module: Service Escalations | 1 | Pending
49 | 2005-07-17 | RFE | servicedependencies.pl | New module: Service Dependencies | 1 | Pending
50 | 2005-07-17 | RFE | hostgroupescalations.pl | New module: Hostgroup Escalations | 1 | Pending
52 | 2005-07-17 | RFE | hostescalations.pl | New module: Host Escalations | 1 | Pending
53 | 2005-07-17 | RFE | hostdependencies | New module: Hostdependencies.pl | 1 | Pending
56 | 2005-07-17 | RFE | resources | Adding extra variables for dbsupport | 1 | Pending
61 | 2005-07-17 | RFE | config.pl | New module: modify ncpl config via webinterface | 1 | Pending
39 | 2005-08-18 | RFE | services.pl | New module: services.pl | 1 | Done
62 | 2005-07-17 | RFE | perfparse.pl | New module: perfparse configuration | 1 | Pending
1 | 2005-10-15 | RFE | NCPL_SESSIONS.pm | Your session timed out, please login again! | 1 | Pending
2 | 2005-10-15 | RFE | NCPL_DATABASE.pm | ListAllRecords(): change order of variables | 1 | Pending
3 | 2005-10-15 | RFE | NCPL_DATABASE.pm | $filterkey -> $filterfield (?) | 1 | Pending
6 | 2005-10-15 | RFE | NCPL_SESSIONS.pm | Userlevel implementation and checking | 1 | Pending
8 | 2005-10-15 | RFE | GENERAL | $SQL_CATEGORIES | 1 | Pending
14 | 2005-10-15 | RFE | tools.pl | Automatic creation of service dependencies based on '+ping' | 1 | Pending
21 | 2005-10-15 | RFE | install.pl | Email notification on new config install | 1 | Done
35 | 2005-10-15 | RFE | ondemand.pl | New module: running ondemand checks | 1 | Done
36 | 2005-10-15 | RFE | tools.pl | NSLOOKUP for hosts | 1 | Done
15 | 2005-10-15 | RFE | GENERAL | Perl code cleanup | 1 | Pending
18 | 2005-10-20 | RFE | GENERAL | Scheduling of end of life (delete flag met datum) | 1 | Pending
19 | 2005-10-20 | Doc | GENERAL | Write documentation | 1 | Pending
37 | 2005-10-20 | RFE | GENERAL | Support for distributed nagios configurations | 1 | Pending
38 | 2005-10-20 | RFE | GENERAL | Support for remote system configs | 1 | Pending
20 | 2005-10-27 | RFE | tools.pl | Rename function for hosts | 1 | Pending
27 | 2005-10-27 | RFE | NCPL_EXPORT.pm | Confirmation screen with sync options, nagiosbydb (checkboxes) | 1 | Pending
29 | 2005-10-27 | RFE | tools.pl | Traceroute implementation and automatic parent detection | 1 | Pending
32 | 2005-11-02 | RFE | tools.pl | Adding new servers via a "wizzard" | 1 | Pending
63 | 2005-11-02 | RFE | NCPL_HTML.pm | Combobox based on hashes | 1 | Pending
64 | 2005-11-02 | RFE | NCPL_HTML.pm | File upload implementation | 1 | Pending
65 | 2005-11-02 | RFE | NCPL_HTML.pm | Datepicker implementation | 1 | Pending
66 | 2005-11-02 | RFE | NCPL_IMPORT.pm | Config file upload feature | 1 | Pending
67 | 2005-11-03 | RFE | GENERAL | "Item used in" implementation | 1 | Pending
68 | 2005-11-03 | RFE | GENERAL | Javascript form validation | 1 | Pending
69 | 2005-11-04 | RFE | GENERAL | Move .pm files to a special directory (not cgi-bin) | 1 | Pending
71 | 2005-11-04 | Bugfix | NCPL_EXPORT.pm | Use $server_name in all export query's | 5 | Done
70 | 2005-11-04 | RFE | GENERAL | Split and move .conf files to a special directory (not cgi-bin) | 1 | Pending
73 | 2005-11-04 | RFE | install.pl | Send only mail when there are files who differ | 1 | Done
74 | 2005-11-04 | RFE | REPORTS | New module: reports.pl | 1 | Pending
75 | 2005-11-05 | RFE | nrpe.pl | New module: nrpe.pl | 1 | Pending
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100